## Portfolio
Portfolio | ProjectDepartments | EnterpriseProjectTypeName | ProjectName
Improve Infrastructure | Clinical Data Management | Application Upgrade/Implementation | Modify Billing System to match revised ICD code sets
Improve Infrastructure | Medical Device Services | Application Upgrade/Implementation | Resource Scheduling System Upgrade
Provide Information | Medical Device Services | Data Governance Project Implementation | Clinical Device Management Program Implementation
Service | Clinical Data Management | Data Governance Project Implementation | Data Governance Project Services
Improve Infrastructure | Patient Care IT Operations | Infrastructure/Equipment Upgrade | Standardize enrollment
Reduce Expenses | Clinical Data Management | Electronic Medical Records | Medical Record Migration
Provide Information | Systems Education Services | Infrastructure Setup (op theater, clinic, service, etc.) | Clinical Systems Education Program Implementation
Provide Information | Clinical Data Management | Electronic Medical Records | Electronic Patient Record Migration
Reduce Expenses | Clinical Data Management | Electronic Medical Records | Clinical Data Security Upgrade
Reduce Expenses | Radiology | Infrastructure Setup (op theater, clinic, service, etc.) | CarePlus Infrastructure, Hardware, and Licensing
Improve Customer Retention | Clinical Data Management | Application Upgrade/Implementation | Information Exchange with Enrollment system
Improve Infrastructure | Medical Device Services | Hospital Construction | Construct Neurology Clinic
Create Competitive Advantages | Patient Care IT Operations | Enterprise Project | VAPR
Product Innovation | Patient Care IT Operations | Application Upgrade/Implementation | General Point-of-Care System Implementation
Create Competitive Advantages |  | HIPAA Compliance Implementation | HIPAA Data Compliance Implementation
Service | Clinical Data Management | Application Upgrade/Implementation | Clinical Applications Bug Fix
Provide Information | Medical Device Services | Infrastructure Setup (op theater, clinic, service, etc.) | Enable Pre-Screening Mobile Device Platforms
Reduce Expenses | Clinical Data Management | Electronic Medical Records | Modernize Segment Member materials
Provide Information | System Support Services | Electronic Medical Records | Outpatient System Integration
Product Innovation | Medical Device Services | Infrastructure/Equipment Upgrade | Enhanced Encounter Submission Capability
Improve Infrastructure | Medical Device Services | Application Upgrade/Implementation | Glucose Monitor Support System Implementation
Create Competitive Advantages | Critical Care | Infrastructure Setup (op theater, clinic, service, etc.) | Urgent Care Infrastructure Setup
Improve Infrastructure | IT | Infrastructure Setup (op theater, clinic, service, etc.) | Implement cloud-based infrastructure
Service |  | SJ1 | Teams Integration Project
Improve Infrastructure |  | Enterprise Project | EMR Updates
Service |  | SJ1 | Project-Teams Integration Test 1 - USA Central
Service |  | SJ1 | Project-Teams Integration Test 2 - USA East
Product Innovation |  | Enterprise Project | Annual Nurse Conference
Product Innovation |  | Enterprise Project | Modernize member materials
Product Innovation | System Support Services | HIPAA Compliance Implementation | Doctor Portal
Provide Information |  | Enterprise Project | Medical Records Mgmt - Provider Data Validation
Provide Information | System Support Services | Infrastructure/Equipment Upgrade | Standardize Group Enrollment
Service | Patient Care IT Operations | Enterprise Project | Application Networking Services Impatient Implementation Level 1
Provide Information |  | Enterprise Project | Information Exchange with Encounter Service
Provide Information |  | Enterprise Project | Modernize Reporting [APas]
Cut Costs |  | Enterprise Project | Feature program on MyHumana main page
Cut Costs |  | Enterprise Project | Feature 2 program on MyHumana main page
Cut Costs |  | Enterprise Project | Add mobile notification about e-delivery program
Cut Costs |  | Enterprise Project | Product Milestones
Cut Costs |  | Enterprise Project | Project Master Plan
Reduce Expenses |  | Enterprise Project | Tax Prep
Timesheet Administrative Work Items
Improve Infrastructure | Patient Care IT Operations | Application Upgrade/Implementation | In patient Systems Upgrades
Improve Customer Retention |  | Application Upgrade/Implementation | Grow Kindred @ Home - Demonstrate Value to Plan
Improve Customer Retention | System Support Services | Application Upgrade/Implementation | Continue to expand PiPC
Improve Customer Retention | Radiology | Application Upgrade/Implementation | Delivery Longitudinal Health Records
Create Competitive Advantages | System Support Services | Application Upgrade/Implementation | AgileFall
Create Competitive Advantages | Cardiology | Infrastructure/Equipment Upgrade | Cardiology Equipment Upgrade

## Portfolio-Timeline
ProjectName | TaskIsMilestone | ProjectStartDate | Earliest Finish Date | Earliest Timeline Milestone Date | ProjectBaselineFinishDate | ProjectBaselineStartDate | P_% Complete | Program Timeline Category | Timeline Milestone
Tax Prep | FALSE | 2020-01-06 | 2020-10-19 |  | 2020-10-20 17:00 | 2020-07-08 08:00 | 0.15 | Tax Prep
Tax Prep | TRUE | 2020-01-06 | 2020-10-19 |  | 2020-10-20 17:00 | 2020-07-08 08:00 | 0.15
Tax Prep | TRUE | 2020-01-06 | 2020-10-19 | 2020-07-15 | 2020-10-20 17:00 | 2020-07-08 08:00 | 0.15 | Analysis Complete | 2nd Review Completed
HIPAA Data Compliance Implementation | FALSE | 2020-02-01 | 2021-02-16 |  | 2020-12-10 17:00 | 2020-02-03 08:00 | 0.4 | HIPAA Data Compliance Implementation
HIPAA Data Compliance Implementation | TRUE | 2020-02-01 | 2021-02-16 |  | 2020-12-10 17:00 | 2020-02-03 08:00 | 0.4
HIPAA Data Compliance Implementation | TRUE | 2020-02-01 | 2021-02-16 | 2021-02-16 | 2020-12-10 17:00 | 2020-02-03 08:00 | 0.4 | Deployment Complete | Implementations Complete
HIPAA Data Compliance Implementation | TRUE | 2020-02-01 | 2021-02-16 | 2020-09-29 | 2020-12-10 17:00 | 2020-02-03 08:00 | 0.4 | Development Complete | Development Complete
General Point-of-Care System Implementation | FALSE | 2020-06-01 | 2020-10-16 |  | 2020-10-16 17:00 | 2020-06-01 08:00 | 0.61 | General Point-of-Care System Implementation
General Point-of-Care System Implementation | TRUE | 2020-06-01 | 2020-10-16 |  | 2020-10-16 17:00 | 2020-06-01 08:00 | 0.61
Medical Record Migration | FALSE | 2020-06-01 | 2020-09-17 |  | 2020-09-17 15:00 | 2020-06-01 08:00 | 0.71 | Medical Record Migration
Medical Record Migration | TRUE | 2020-06-01 | 2020-09-17 |  | 2020-09-17 15:00 | 2020-06-01 08:00 | 0.71
Medical Record Migration | TRUE | 2020-06-01 | 2020-09-17 | 2020-09-16 | 2020-09-17 15:00 | 2020-06-01 08:00 | 0.71 | Deployment Complete | Migration Complete
Modernize Segment Member materials | FALSE | 2020-06-01 | 2020-09-18 |  | 2020-09-18 17:00 | 2020-06-01 08:00 | 0.74 | Modernize Segment Member materials
Modernize Segment Member materials | TRUE | 2020-06-01 | 2020-09-18 |  | 2020-09-18 17:00 | 2020-06-01 08:00 | 0.74
Modernize Segment Member materials | TRUE | 2020-06-01 | 2020-09-18 | 2020-08-14 | 2020-09-18 17:00 | 2020-06-01 08:00 | 0.74 | Development Complete | Development Complete
Enhanced Encounter Submission Capability | FALSE | 2020-08-03 | 2020-12-18 |  | 2020-12-18 12:00 | 2020-08-03 08:00 | 0.1 | Enhanced Encounter Submission Capability
Enhanced Encounter Submission Capability | TRUE | 2020-08-03 | 2020-12-18 |  | 2020-12-18 12:00 | 2020-08-03 08:00 | 0.1

## Birds-on-a-wire
Project Name | Parent Task | TaskIsMilestone | Parent Task Start Date | Earliest Parent Task Finish Date | Earliest Milestone Date | Timeline Category | Timeline Bar 2 | Milestone
58-05782 - Pre-Clinical | Investigator Brochures | FALSE | 2020-02-01 08:00 | 2020-02-24 17:00 |  | Parent Task | Parent Task
58-05782 - Pre-Clinical | Investigator Brochures | TRUE | 2020-02-01 08:00 | 2020-02-24 17:00 | 2020-02-24 17:00 | Pre-clinical document complete |  | IB Complete
58-05782 - Pre-Clinical | Investigator Brochures | TRUE | 2020-02-01 08:00 | 2020-02-24 17:00 | 2020-02-01 08:00 | Pre-clinical document initiation |  | IB initiation
58-05782 - Pre-Clinical | Investigator Brochures | TRUE | 2020-02-01 08:00 | 2020-02-24 17:00 | 2020-02-18 17:00 | Pre-clinical document review complete |  | IB Review Complete
58-05782 - Pre-Clinical | Investigator Brochures | TRUE | 2020-02-01 08:00 | 2020-02-24 17:00 | 2020-02-11 08:00 | Pre-clinical draft complete |  | IB Draft
58-05782 - Pre-Clinical | Clinical Study Protocols | FALSE | 2020-02-24 17:00 | 2020-03-20 17:00 |  | Parent Task | Parent Task
58-05782 - Pre-Clinical | Clinical Study Protocols | TRUE | 2020-02-24 17:00 | 2020-03-20 17:00 | 2020-03-20 17:00 | Pre-clinical document complete |  | CSP Complete
58-05782 - Pre-Clinical | Clinical Study Protocols | TRUE | 2020-02-24 17:00 | 2020-03-20 17:00 | 2020-02-24 17:00 | Pre-clinical document initiation |  | CSP initiation
58-05782 - Pre-Clinical | Clinical Study Protocols | TRUE | 2020-02-24 17:00 | 2020-03-20 17:00 | 2020-03-12 17:00 | Pre-clinical document review complete |  | CSP Review Complete
58-05782 - Pre-Clinical | Clinical Study Protocols | TRUE | 2020-02-24 17:00 | 2020-03-20 17:00 | 2020-03-04 08:00 | Pre-clinical draft complete |  | CSP Draft
58-05782 - Pre-Clinical | Informed Consent Form | FALSE | 2020-03-20 17:00 | 2020-04-09 17:00 |  | Parent Task | Parent Task
58-05782 - Pre-Clinical | Informed Consent Form | TRUE | 2020-03-20 17:00 | 2020-04-09 17:00 | 2020-04-09 17:00 | Pre-clinical document complete |  | ICF Complete
58-05782 - Pre-Clinical | Informed Consent Form | TRUE | 2020-03-20 17:00 | 2020-04-09 17:00 | 2020-03-20 17:00 | Pre-clinical document initiation |  | ICF initiation
58-05782 - Pre-Clinical | Informed Consent Form | TRUE | 2020-03-20 17:00 | 2020-04-09 17:00 | 2020-04-02 17:00 | Pre-clinical document review complete |  | ICF Review Complete
58-05782 - Pre-Clinical | Informed Consent Form | TRUE | 2020-03-20 17:00 | 2020-04-09 17:00 | 2020-03-30 08:00 | Pre-clinical draft complete |  | ICF Draft
58-00365 - Pre-Clinical | Investigator Brochures | FALSE | 2020-04-02 08:00 | 2020-04-16 17:00 |  | Parent Task | Parent Task
58-00365 - Pre-Clinical | Investigator Brochures | TRUE | 2020-04-02 08:00 | 2020-04-16 17:00 | 2020-04-16 17:00 | Pre-clinical document complete |  | IB Complete
58-00365 - Pre-Clinical | Investigator Brochures | TRUE | 2020-04-02 08:00 | 2020-04-16 17:00 | 2020-04-02 08:00 | Pre-clinical document initiation |  | IB initiation
58-00365 - Pre-Clinical | Investigator Brochures | TRUE | 2020-04-02 08:00 | 2020-04-16 17:00 | 2020-04-13 17:00 | Pre-clinical document review complete |  | IB Review Complete
58-00365 - Pre-Clinical | Investigator Brochures | TRUE | 2020-04-02 08:00 | 2020-04-16 17:00 | 2020-04-07 08:00 | Pre-clinical draft complete |  | IB Draft
58-00365 - Pre-Clinical | Clinical Study Protocols | FALSE | 2020-04-16 17:00 | 2020-05-04 17:00 |  | Parent Task | Parent Task
58-00365 - Pre-Clinical | Clinical Study Protocols | TRUE | 2020-04-16 17:00 | 2020-05-04 17:00 | 2020-05-04 17:00 | Pre-clinical document complete |  | CSP Complete
58-00365 - Pre-Clinical | Clinical Study Protocols | TRUE | 2020-04-16 17:00 | 2020-05-04 17:00 | 2020-04-16 17:00 | Pre-clinical document initiation |  | CSP initiation
58-00365 - Pre-Clinical | Clinical Study Protocols | TRUE | 2020-04-16 17:00 | 2020-05-04 17:00 | 2020-04-29 17:00 | Pre-clinical document review complete |  | CSP Review Complete
58-00365 - Pre-Clinical | Clinical Study Protocols | TRUE | 2020-04-16 17:00 | 2020-05-04 17:00 | 2020-04-22 08:00 | Pre-clinical draft complete |  | CSP Draft
58-00365 - Pre-Clinical | Informed Consent Form | FALSE | 2020-05-04 17:00 | 2020-05-20 17:00 |  | Parent Task | Parent Task
58-00365 - Pre-Clinical | Informed Consent Form | TRUE | 2020-05-04 17:00 | 2020-05-20 17:00 | 2020-05-20 17:00 | Pre-clinical document complete |  | ICF Complete
58-00365 - Pre-Clinical | Informed Consent Form | TRUE | 2020-05-04 17:00 | 2020-05-20 17:00 | 2020-05-04 17:00 | Pre-clinical document initiation |  | ICF initiation
58-00365 - Pre-Clinical | Informed Consent Form | TRUE | 2020-05-04 17:00 | 2020-05-20 17:00 | 2020-05-14 17:00 | Pre-clinical document review complete |  | ICF Review Complete
58-00365 - Pre-Clinical | Informed Consent Form | TRUE | 2020-05-04 17:00 | 2020-05-20 17:00 | 2020-05-11 08:00 | Pre-clinical draft complete |  | ICF Draft

## Project-Health-Timeline
ProjectName | TaskIsMilestone | ProjectStartDate | Earliest Finish Date | ProjectPercentCompleted | Earliest Timeline Milestone Date | Project Health Timeline Category | Timeline Milestone
Standardize Group Enrollment | FALSE | 2019-11-15 | 2020-09-11 | 60 |  | Yellow
Standardize Group Enrollment | TRUE | 2019-11-15 | 2020-09-11 | 60
HIPAA Data Compliance Implementation | FALSE | 2020-02-01 | 2021-02-16 | 40 |  | Red
HIPAA Data Compliance Implementation | TRUE | 2020-02-01 | 2021-02-16 | 40
HIPAA Data Compliance Implementation | TRUE | 2020-02-01 | 2021-02-16 | 40 | 2021-02-16 | Deployment Complete | Implementations Complete
HIPAA Data Compliance Implementation | TRUE | 2020-02-01 | 2021-02-16 | 40 | 2020-09-29 | Development Complete | Development Complete
Information Exchange with Encounter Service | FALSE | 2020-03-16 | 2021-02-15 | 50 |  | Green
General Point-of-Care System Implementation | FALSE | 2020-06-01 | 2020-10-16 | 61 |  | Green
General Point-of-Care System Implementation | TRUE | 2020-06-01 | 2020-10-16 | 61
Enhanced Encounter Submission Capability | FALSE | 2020-08-03 | 2020-12-18 | 10 |  | Yellow
Enhanced Encounter Submission Capability | TRUE | 2020-08-03 | 2020-12-18 | 10
Cardiology Equipment Upgrade | FALSE | 2020-10-05 | 2021-01-01 | 0 |  | Green
Cardiology Equipment Upgrade | TRUE | 2020-10-05 | 2021-01-01 | 0
Cardiology Equipment Upgrade | TRUE | 2020-10-05 | 2021-01-01 | 0 | 2021-01-01 | Deployment Complete | Upgrade Comoplete
Cardiology Equipment Upgrade | TRUE | 2020-10-05 | 2021-01-01 | 0 | 2020-11-06 | Planning Complete | Planning Complete

## Project-Phases
ProjectName | TaskIsMilestone | ProjectPhaseStart | Earliest ProjectPhase Finish Date | TaskPercentCompleted | ProjectBaselinePhaseFinish | ProjectBaselinePhaseStart | ProjectPhase | TopParentTask
Data Governance Project Services | FALSE | 2020-05-01 | 2020-07-23 | 100 | 2020-07-23 17:00 | 2020-05-01 08:00 | Planning | Planning
Information Exchange with Enrollment system | FALSE | 2020-06-01 | 2020-09-17 | 71 | 2020-08-11 17:00 | 2020-06-01 08:00 | Planning | Planning
Data Governance Project Services | FALSE | 2020-08-04 | 2020-10-26 | 22 | 2020-10-26 17:00 | 2020-07-24 08:00 | Development | Development
Information Exchange with Enrollment system | FALSE | 2020-09-18 | 2020-12-04 | 0 | 2020-10-28 17:00 | 2020-08-12 08:00 | Development | Development
Electronic Patient Record Migration | FALSE | 2020-09-21 | 2020-10-23 | 0 | 2020-10-23 17:00 | 2020-09-21 08:00 | Planning | Planning
Cardiology Equipment Upgrade | FALSE | 2020-10-05 | 2020-11-06 | 0 | 2020-11-06 17:00 | 2020-10-05 08:00 | Planning | Planning
Clinical Applications Bug Fix | FALSE | 2020-10-20 | 2021-03-15 | 0 |  |  | Planning | Planning
Electronic Patient Record Migration | FALSE | 2020-10-26 | 2021-03-05 | 0 | 2021-03-05 17:00 | 2020-10-26 08:00 | Development | Development
Data Governance Project Services | FALSE | 2020-10-27 | 2021-06-14 | 0 | 2021-06-14 17:00 | 2020-10-27 08:00 | Implementation | Implementation
Cardiology Equipment Upgrade | FALSE | 2020-11-09 | 2020-12-25 | 0 | 2020-12-25 17:00 | 2020-11-09 08:00 | Development | Development
Information Exchange with Enrollment system | FALSE | 2020-12-07 | 2021-02-08 | 0 | 2020-12-31 17:00 | 2020-10-29 08:00 | Implementation | Implementation
Electronic Patient Record Migration | FALSE | 2021-03-08 | 2021-05-14 | 0 | 2021-05-14 17:00 | 2021-03-08 08:00 | Migration | Migration
Clinical Applications Bug Fix | FALSE | 2021-03-16 | 2021-05-17 | 0 |  |  | Analysis | Analysis
Clinical Applications Bug Fix | FALSE | 2021-05-18 | 2021-09-06 | 0 |  |  | Solution Implementation | Solution Implementation

## Resource-Timeline
Project Name | Resource Name | TaskIsMilestone | Earliest TaskFinishDate | TaskStartDate | TaskPriority | TaskName
Data Parsing Tool | Chris Barry | FALSE | 2020-03-16 08:00 | 2020-02-18 08:00 | Critical | Conduct needs analysis
Data Parsing Tool | David Pelton | FALSE | 2020-03-16 08:00 | 2020-02-18 08:00 | Critical | Conduct needs analysis
Data Parsing Tool | Brian Groth | FALSE | 2020-03-16 17:00 | 2020-02-29 08:00 | Major | Determine project scope
Data Parsing Tool | Chris Barry | FALSE | 2020-04-04 17:00 | 2020-03-18 08:00 | Minor | Develop functional specifications
Data Parsing Tool | David Pelton | FALSE | 2020-04-14 08:00 | 2020-03-18 08:00 | Major | Develop preliminary budget
Data Parsing Tool | Brian Groth | FALSE | 2020-04-18 08:00 | 2020-03-18 17:00 | Major | Secure project sponsorship
Hub Upgrade | Denise Smith | FALSE | 2020-04-08 08:00 | 2020-03-22 08:00 | Critical | Develop code
Apparel Upgrade | Luis Bonifaz | FALSE | 2020-04-27 08:00 | 2020-04-06 08:00 | Critical | Deploy infrastructure components
Apparel Upgrade | Michael Patten | FALSE | 2020-04-27 08:00 | 2020-04-06 08:00 | Critical | Deploy infrastructure components
Data Parsing Tool | Chris Barry | FALSE | 2020-04-30 17:00 | 2020-04-06 08:00 | Minor | Review functional specifications
Hub Upgrade | Denise Smith | FALSE | 2020-04-28 08:00 | 2020-04-09 08:00 | Minor | Review modular code
Hub Upgrade | Gatis Ozolins | FALSE | 2020-04-28 08:00 | 2020-04-09 08:00 | Minor | Review modular code
Apparel Upgrade | Luis Bonifaz | FALSE | 2020-05-15 08:00 | 2020-04-29 08:00 | Major | Test infrastructure component
Apparel Upgrade | Michael Patten | FALSE | 2020-05-15 08:00 | 2020-04-29 08:00 | Major | Test infrastructure component
Hub Upgrade | Denise Smith | FALSE | 2020-05-25 08:00 | 2020-04-29 08:00 | Major | Test module integration
Hub Upgrade | Gatis Ozolins | FALSE | 2020-05-25 08:00 | 2020-04-29 08:00 | Major | Test module integration
Apparel Upgrade | Luis Bonifaz | FALSE | 2020-05-31 08:00 | 2020-05-17 08:00 | Minor | Evaluate pilot feedback
Apparel Upgrade | Michael Patten | FALSE | 2020-06-03 08:00 | 2020-05-17 08:00 | Major | Post implementation review

## Single-Line-View
Project | TaskIsMilestone | Start Date | Earliest Due Date | Data Label | Earliest Start Date | Priority | Task Name
Define the opportunity | FALSE | 2020-10-19 | 2020-10-31 |  | 2020-10-19 | Low | Identify available info
Define the opportunity | FALSE | 2020-10-31 | 2020-11-19 |  | 2020-10-31 | Medium | Research new technologies
Evaluate Business Approach | FALSE | 2020-10-31 | 2020-11-17 |  | 2020-10-31 | Urgent | Define new entity requirements
Evaluate Risks and Rewards | FALSE | 2020-11-15 | 2020-11-29 |  | 2020-11-15 | Urgent | Estimate the competition
Evaluate Business Approach | FALSE | 2020-11-17 | 2020-12-05 |  | 2020-11-17 | Low | Research acquisition potential
Define the opportunity | TRUE | 2020-11-21 | 2020-11-21 | Research Complete | 2020-11-21 | Important | Research Complete
Define the opportunity | FALSE | 2020-11-23 | 2020-12-06 |  | 2020-11-23 | Low | Interview business owners
Evaluate Risks and Rewards | FALSE | 2020-11-29 | 2020-12-17 |  | 2020-11-29 | Medium | Assess needed resources availability
Evaluate Business Approach | FALSE | 2020-12-05 | 2020-12-16 |  | 2020-12-05 | Medium | Break-even analysis
Define the opportunity | FALSE | 2020-12-06 | 2020-12-21 |  | 2020-12-06 | Urgent | Identify operating costs
Evaluate Risks and Rewards | FALSE | 2020-12-17 | 2021-01-04 |  | 2020-12-17 | Urgent | Review & modify strategic plan
Evaluate Business Approach | TRUE | 2020-12-18 | 2020-12-18 | Phase 2 Complete | 2020-12-18 | Important | Phase 2 Complete
Define the opportunity | TRUE | 2020-12-23 | 2020-12-23 | Phase 1 Complete | 2020-12-23 | Medium | Phase 1 Complete
Evaluate Risks and Rewards | TRUE | 2021-01-06 | 2021-01-06 | Phase 3 Complete | 2021-01-06 | Medium | Phase 3 Complete

## Waterfall-View
Project | Task Name | TaskIsMilestone | Start Date | Earliest Due Date | Earliest Start Date | Priority | Data Label | Assigned to | Percent_Complete
Define the opportunity | Identify available info | FALSE | 2020-10-19 | 2020-10-31 | 2020-10-19 | Low |  | Shreyas Gokhale | 1
Define the opportunity | Research new technologies | FALSE | 2020-10-31 | 2020-11-19 | 2020-10-31 | Medium |  | Molly Clark | 0.5
Evaluate Business Approach | Define new entity requirements | FALSE | 2020-10-31 | 2020-11-17 | 2020-10-31 | Urgent |  | Shreyas Gokhale | 1
Evaluate Risks and Rewards | Estimate the competition | FALSE | 2020-11-15 | 2020-11-29 | 2020-11-15 | Urgent |  | Shreyas Gokhale | 1
Evaluate Business Approach | Research acquisition potential | FALSE | 2020-11-17 | 2020-12-05 | 2020-11-17 | Low |  | Jeff Spencer | 0.5
Define the opportunity | Research Complete | TRUE | 2020-11-21 | 2020-11-21 | 2020-11-21 | Important | Research Complete |  | 0
Define the opportunity | Interview business owners | FALSE | 2020-11-23 | 2020-12-06 | 2020-11-23 | Low |  | Molly Clark | 0
Evaluate Risks and Rewards | Assess needed resources availability | FALSE | 2020-11-29 | 2020-12-17 | 2020-11-29 | Medium |  | Jeff Spencer | 0.5
Evaluate Business Approach | Break-even analysis | FALSE | 2020-12-05 | 2020-12-16 | 2020-12-05 | Medium |  | Jeff Spencer | 0
Define the opportunity | Identify operating costs | FALSE | 2020-12-06 | 2020-12-21 | 2020-12-06 | Urgent |  | Jamie Reding | 0
Evaluate Risks and Rewards | Review & modify strategic plan | FALSE | 2020-12-17 | 2021-01-04 | 2020-12-17 | Urgent |  | Jeff Spencer | 0
Evaluate Business Approach | Phase 2 Complete | TRUE | 2020-12-18 | 2020-12-18 | 2020-12-18 | Important | Phase 2 Complete |  | 0
Define the opportunity | Phase 1 Complete | TRUE | 2020-12-23 | 2020-12-23 | 2020-12-23 | Medium | Phase 1 Complete |  | 0
Evaluate Risks and Rewards | Phase 3 Complete | TRUE | 2021-01-06 | 2021-01-06 | 2021-01-06 | Medium | Phase 3 Complete |  | 0